PROFORMA FOR SUBMITTING HALF YEARLY PROGRESS REPORT IN RESPECT OF RESEARCH GRANTS RELEASED BY RGUHS FOR THE YEAR .....2022 -2023..

……Half yearly (FIRST)…..REPORT (FIRST/SECOND/THIRD)       Date: 18/12/2023

| 1. | Faculty | AYURVEDA |
| --- | --- | --- |
| 2. | Name of the Principal Investigator | Dr. Pushpavati. S. Policepatil M.S(Ayu) Professor, Department of Shalakya Tantra BVVS Ayurved Medical College and Hospital Bagalkot-587101. |
| 3. | Name and address of the Institution | BVVS Ayurved Medical College and Hospital Bvvs old campus Bagalkot-587101. |
| 4. | Title of the proposal | “A Randomized comparative clinical study to evaluate the efficacy of Panchapallava Gel and Stomatab Gel in Pittaja Mukapaka with Special reference to Aphthous Ulcer”. |
| 5 | Project code | 22AYU022 |
| 6. | Details of the release of first instalment amount |  |
|  | Cheque No. | NEFT-CIUB-CIUBH23 |
|  | Date: | 22/06/23 |
|  | Amount: | 40,000/- |
| 7. | Objectives set out for the Study | 1. To prepare Panchapallava Gel. 2.To known the efficacy of Panchapallava Gel in Pittaja Mukapaka. 3.To known the efficacy of Stomatab Gel in Pittaja Mukapaka |
| 8. | Any modifications done to the research proposal submitted to RGUHS. If yes give details. | No changes made |
| 9. | Details of the progress so far made in the Study including the verifiable indicators | First 6 months 1. Preparation of medicine. 2.Preparing case sheet |
| 10. | Plan of action for the remaining part of the study | After 1 year - Completion of Medicine Preparation - Conducting Health Camps. - Conducting Research study. After 1 ½ year 1. Completion of research Study. 2. Paper Presentation in National Seminars. End of 2nd year 1. Publication of research Article In National/International conferences 2. Submission of Final Report |
| 11. | The amount of grants utilized so far out of the released first instalment | NOT YET UTILIZED |
| 12. | If the first instalment is not completely utilized, the probable time at which second instalment is required | Requirement of the 2nd installement will be by May 2024 |
| 13 | Period of the study | 2 years |
| 14 | Any other relevant information PI wishes to mention | NO |

Note: All the data collected should be made available to the Monitoring Committee at the time of inspection along with relevant records pertaining to research.

- Signature of the PI

- Signature of the Co-Investigator

- Signature of the Head of the Institution