**PROFORMA FOR SUBMITTING HALF YEARLY PROGRESS REPORT IN RESPECT OF RESEARCH GRANTS RELEASED BY RGUHS FOR THE YEAR .....2022 -2023..**

**……Half yearly (FIRST)…..REPORT (FIRST/SECOND/THIRD) Date: 18/12/2023**

|  |  |  |
| --- | --- | --- |
| 1. | Faculty | **AYURVEDA** |
| 2. | Name of the Principal Investigator | Dr. Pushpavati. S. Policepatil M.S(Ayu)  Professor, Department of Shalakya Tantra  BVVS Ayurved Medical College and Hospital Bagalkot-587101. |
| 3. | Name and address of the Institution | BVVS Ayurved Medical College and Hospital Bvvs old campus Bagalkot-587101. |
| 4. | Title of the proposal | “A Randomized comparative clinical study to evaluate the efficacy of Panchapallava Gel and Stomatab Gel in Pittaja Mukapaka with Special reference to Aphthous Ulcer”. |
| 5 | Project code | **22AYU022** |
| 6. | Details of the release of first instalment amount |  |
| Cheque No. | NEFT-CIUB-CIUBH23 |
| Date: | 22/06/23 |
| Amount: | 40,000/- |
| 7. | Objectives set out for the Study | 1. To prepare Panchapallava Gel.  2.To known the efficacy of  Panchapallava Gel in Pittaja  Mukapaka.  3.To known the efficacy of Stomatab  Gel in Pittaja Mukapaka |
| 8. | Any modifications done to the research proposal submitted to RGUHS. If yes give details. | No changes made |
| 9. | Details of the progress so far made in the Study including the verifiable indicators | **First 6 months**    1. Preparation of medicine.  2.Preparing case sheet |
| 10. | Plan of action for the remaining part of the study | **After 1 year**   1. Completion of Medicine Preparation 2. Conducting Health Camps. 3. Conducting Research study.   **After 1 ½ year**  1. Completion of research Study.  2. Paper Presentation in National  Seminars.  **End of 2nd year**  1. Publication of research Article In  National/International  conferences  2. Submission of Final Report |
| 11. | The amount of grants utilized so far out of the released first instalment | NOT YET UTILIZED |
| 12. | If the first instalment is not completely utilized, the probable time at which second instalment is required | Requirement of the 2nd installement will be by May 2024 |
| 13 | Period of the study | 2 years |
| 14 | Any other relevant information PI wishes to mention | NO |

**Note:** All the data collected should be made available to the Monitoring Committee at the time of inspection along with relevant records pertaining to research.

1. Signature of the PI
2. Signature of the Co-Investigator
3. Signature of the Head of the Institution